## Slide 1: Construction Contracts
General Concepts and Understanding

## Slide 2: Construction Contract Types
Agenda
Design-Bid-Build
Design-Build
Construction Management
Notes: Project owner typically begins by engaging an architect and/or an engineer, which may consist of any or all services necessary to take the project from the conceptual design stage through final design of the project and the preparation of construction documents.
Regardless of whether the owner is a private or a public entity, the design professionals are generally selected based on their qualifications, and then engaged through a process of negotiation, as opposed to competitive bidding.
Advantages: Design work is finished before a contractor is selected, which permits the contractor to be selected based on competitive bids for a precisely-defined scope of work.
Disadvantages: The contractor is not involved in the design process, making meaningful and timely input on issues such as choice of materials, constructability and pricing not likely to be available.
“Fast Track” construction is not an option. Bidders unlikely to suggest project improvements in order to avoid price increases that might make the contractor’s price less competitive.

## Slide 3: Construction Contracts
Design-Bid-Build
Multiple Stages
Entity that designs is different from that who completes construction
Advantages
Design work is finished before a contractor is selected
Contractor selected based on competitive bids for a precisely-defined scope of work
Disadvantages
Contractor is not involved in the design process
Notes: Project owner typically begins by engaging an architect and/or an engineer, which may consist of any or all services necessary to take the project from the conceptual design stage through final design of the project and the preparation of construction documents.
Regardless of whether the owner is a private or a public entity, the design professionals are generally selected based on their qualifications, and then engaged through a process of negotiation, as opposed to competitive bidding.
Advantages: Design work is finished before a contractor is selected, which permits the contractor to be selected based on competitive bids for a precisely-defined scope of work.
Disadvantages: The contractor is not involved in the design process, making meaningful and timely input on issues such as choice of materials, constructability and pricing not likely to be available.
“Fast Track” construction is not an option. Bidders unlikely to suggest project improvements in order to avoid price increases that might make the contractor’s price less competitive.

## Slide 4: Construction Contracts
Design-Build
Design and construction by single entity
Advantages
Design and construction work together as a team from the beginning
Contractor selected based on competitive bids for a precisely-defined scope of work
Disadvantages
May reduce, if not eliminate, competition among contractors
Notes: The design-builder may be, for example, a construction company with design professionals on staff, or a construction company that engages designers for purposes of the project. Joint ventures between design firms and contractors are also sometimes formed for the purpose of contracting with an owner for design-build services.
Advantages: The design and construction professionals are working together as a team from the beginning, and this generally leads to a better, more efficient design reflecting the value engineering generally missing from the design-bid-build project. The owner may look to one entity without regard to whether the problem arises out of the design or the construction. Design-build projects often permit construction to begin as soon as the design-builder is comfortable that the design for the early stages of construction is established.
Disadvantages: Design-Build may reduce, if not eliminate, competition among contractors and the best price thought to flow from such competition. Fear of uncontrolled costs of construction. Owners will not have the security of knowing that the work is being performed by the lowest qualified bidder.

## Slide 5: Construction Contracts
Construction Management
Project delivery method in common use in NH
Hired at or near outset of project
Acts as an agent to the town
Enters into contracts and manages construction
Compensated by either a flat fee, hourly rate, or fixed rate

## Slide 6: Construction Contracts
Construction Management (continued)
Advantages
CM involved early provides options for input on alternative designs, materials, constructability, and value engineering
Disadvantages
During construction phase, tends to resemble traditional design-bid-build model

## Slide 7: Construction Contract Types
Closing
High-Level Understanding of:
    Design-Bid-Build
    Design-Build
    Construction Management
Next Steps

## Slide 8: Construction Management Professional Services
Provides a project’s owner with effective management of the project’s schedule, cost, quality, safety, scope, and function.
At its core, a capital project is made up of three parties (excluding the CM):
    Owner
    Architect /Engineer
    General Contractor
Notes: The owner commissions or funds the project
The architect/engineer designs the project
The general contractor, who oversees day-to-day operations and manages subcontractors